## DB Performance Tuning
# | Action/Recommendation | Details | Status / Notes
1 | Increase Buffer Cache | ADDM and advisory both suggest an increase (e.g., to ~70 GB) | Planning part of CRQ#
2 | Increase PGA | Target exceeded; raise pga_aggregate_target by ~40–50% (Current Size 100GB) | Need to investigate more, probably will work with Oracle
3 | Tune Top I/O SQLs | Especially 4z83wfaxqtdp7, 5yn8skt7tm21p, 22rydaq9zqcxs | Need to be analyzed
4 | Reduce dblink Usage | SQL*Net message from dblink accounts for 2.3% of DB time | Need to take it with SRE
5 | Investigate Parse Contention | Parse CPU to Parse Elapsed 32.87%; check shared pool and cursor usage | Increasing Buffer cache at #1 should take care of this
6 | Review Redo Configuration | Reduce redo log space requests and optimize archive destination. 1. Increase redo size from 1GB to 2GB, 2. Check redo storage performance | Need to revisit - Part of PMX
7 | Tune High-CPU SQLs | 6q6gwbfc78ux7 (TPOP_VALIDATION), 0vqt1a627sdna (DELAYED_ACTIVITIES), gdf06rsgk493z
8 | Cache or Batch Frequent Lookups | SUBSCRIBER_RSOURCE PTN lookups | Need to check
9 | Table Cleanup | Top 10 largest tables | Need to work with SRE